## Sheet1
CSCI 3321 Agile Project Plan
Project Name | Bar-Pop
Project Manager | Bonsignori, Evan [EB]
Project Members: | Bagabas, Ayman [AB]
Bergeron, Kyle [KB]
Nahas, Alsharif Eid [AN]
Patel, Keyur [KP]
Project Deliverable
Scope Statement
Start Date | 2017-08-27
End Date | 2017-12-04
Overall Progress | 9.091%
Task Name | Responsible | Start | End | Days | Status
Sprint 1 |  | 2017-08-27 | 2017-10-03 | 37 | In progress
Assess Requirements | Team [All] | 2017-08-27 | 2017-09-07 | 11 | Complete
Learn Xarmin | Team [All] | 2017-09-07 | 2017-10-05 | 28 | In Progress
Create Xarmin X-Platform Hello World | Team [All] | 2017-09-07 | 2017-10-05 | 28 | In Progress
Write Vision Document | Write - [EB], Diagrams [?], Proofread- [All] | 2017-09-29 | 2017-10-03 | 4 | In Progress [70%]
Sprint 2 |  | 2017-10-05 | 2017-10-12 | 7 | Not started
Create Web Server | [EB] | 2017-10-05 | 2017-10-06 | 1 | Not started
Create Database and Tables for User Registration and Map | [EB][AB] | 2017-10-05 | 2017-10-12 | 7 | Not started
App: User Registration | [KB][KP] | 2017-10-05 | 2017-10-12 | 7 | Not started
App : User Login | [KB][KP] |  |  |  | Can Wait Until Next Sprint
Connect Raspberry PI To Database | [AN][AB] | 2017-10-05 | 2017-10-12 | 7 | Not started
Sprint 3 |  | 2017-10-12 | 2017-10-19 | 7 | Not started
Map View | [EB][KB][KP] | 2017-10-12 | 2017-10-19 | 7 | May Take 2 Sprints
|  | 2017-10-12 | 2017-10-19 | 7 | Not started
Connect Sensor To Raspberry Pi | [AN][AB] | 2017-10-12 | 2017-10-19 | 7 | Not started
Sprint 4 |  | 2017-10-19 | 2017-10-26 | 7 | Not started
Feature 10 |  | 2017-10-19 | 2017-10-26 | 7 | Not started
Feature 11 |  | 2017-10-19 | 2017-10-26 | 7 | Not started
Feature 12 |  | 2017-10-19 | 2017-10-26 | 7 | Not started
Formulas:
Start = [Start, row below]